## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | Knowledge Base Ingestion | Upload PDF/DOCX/TXT/CSV, extract, clean, chunk, embed and index documents. | Must Have | PostgreSQL + pgvector | Development Team | Completed
Sprint 1 | Sprint 1 | US-02 | Validation and Metadata | Validate files, detect duplicates and preserve document/page/chunk metadata. | Must Have | US-01 | Development Team | Completed
Sprint 2 | Sprint 2 | US-03 | Query Understanding Agent | Classify factual, procedural, comparative and ambiguous queries with structured routing. | Must Have | US-01 | Development Team | Completed
Sprint 2 | Sprint 2 | US-04 | Retrieval Agent | Create query embeddings, perform pgvector search, rank Top-K and filter weak evidence. | Must Have | US-01 | Development Team | Completed
Sprint 2 | Sprint 2 | US-05 | Response Generation Agent | Generate grounded answers with source attribution and application confidence. | Must Have | US-04 | Development Team | Completed
Sprint 2 | Sprint 2 | US-06 | Multi-Agent Orchestration | Connect understanding, retrieval and response generation sequentially. | Must Have | US-03, US-04, US-05 | Development Team | Completed
Sprint 2 | Sprint 2 | US-07 | Clarification and Conversation Memory | Handle ambiguous follow-ups and multi-turn context. | Should Have | US-03 | Development Team | Completed
Sprint 2 | Sprint 2 | US-08 | Knowledge Gap Guard | Handle insufficient evidence without unsupported generation. | Must Have | US-04, US-05 | Development Team | Completed
Sprint 2 | Sprint 2 | US-09 | Query Console and Observability | Show query console, retrieval trace, sources, confidence, history and statistics. | Should Have | US-06 | Development Team | Completed
Sprint 2 | Sprint 2 | US-10 | Voice Interface | Browser speech input/output using Web Speech API where supported. | Could Have | Frontend | Development Team | Completed
--- Milestone 3 Sprint Summary ---
Sprint | User Story | Feature | Status | Completed Date | Notes
Sprint 3 | US-M3.1 | Clarification Agent - detects ambiguous queries and asks targeted questions | DONE | 2026-09-23 | 10/10 unit tests pass. Handles pronouns, vague nouns, open-ended follow-ups.
Sprint 3 | US-M3.1 | Clarification cycle - refine_query() merges original + user response | DONE | 2026-09-23 | Pronoun substitution, what-are/how-does patterns implemented.
Sprint 3 | US-M3.2 | Conversation Memory Agent - per-session bounded history (max 10) | DONE | 2026-09-23 | Session isolation, topic tracking, history bounded.
Sprint 3 | US-M3.2 | Pronoun resolution - resolve_references() using active_key_terms | DONE | 2026-09-23 | Bug fix: priority changed from last_entities to active_key_terms. Avoids ACME/boilerplate substitution.
Sprint 3 | US-M3.2 | Topic continuation vs context switch detection | DONE | 2026-09-23 | is_topic_continuation() uses key-term overlap. Empty context returned on switch.
Sprint 3 | US-M3.2 | Clarification state stored in memory per session | DONE | 2026-09-23 | set_clarification_pending/consume_clarification lifecycle working.
Sprint 3 | US-M3.3 | Voice I/O - Speech-to-Text via Web Speech API | DONE | 2026-09-23 | Browser-only. Mic button, transcript, error handling implemented in frontend.
Sprint 3 | US-M3.3 | Voice I/O - Text-to-Speech for answer readback | DONE | 2026-09-23 | TTS controls: play, pause, stop in frontend.
Sprint 3 | US-M3.4 | Transparency Panel - sources with text, page, chunk_id, score, citation | DONE | 2026-09-23 | All 10 M3.4 fields present in every source dict. Text truncated at 600 chars.
Sprint 3 | US-M3.4 | Knowledge Gap handling - confidence=0, controlled response | DONE | 2026-09-23 | No unsupported answers generated when retrieval returns empty.
Sprint 3 | BUG-FIX | retrieval_agent: similarity_threshold default 0.0 -> None | DONE | 2026-09-23 | settings.similarity_threshold now honoured correctly.
Sprint 3 | BUG-FIX | orchestrator: UnboundLocalError resolved_query in clarification path | DONE | 2026-09-23 | resolved_query always assigned: refined_query or memory_resolved_query.
Sprint 3 | BUG-FIX | retrieval_agent: pass resolved_query for vector search | DONE | 2026-09-23 | Pronoun-resolved text now used for embedding, not raw normalized query.
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
SPRINT 1 BACKLOG
US-01 | T1 | Project setup, architecture and repository structure | 19-Aug-2026 | 19-Aug-2026 | Development Team | Completed | 4 | 4 | Day 1: Done
US-01 | T2 | Document upload and file validation | 20-Aug-2026 | 21-Aug-2026 | Development Team | Completed | 8 | 8 | Day 2: Done; Day 3: Done
US-01 | T3 | PDF/DOCX/TXT/CSV extraction | 21-Aug-2026 | 24-Aug-2026 | Development Team | Completed | 10 | 10 | Day 3: Done; Day 4: Done
US-02 | T4 | Cleaning, SHA-256 duplicate detection and metadata | 24-Aug-2026 | 25-Aug-2026 | Development Team | Completed | 8 | 8 | Day 4: Done; Day 5: Done
US-01 | T5 | Chunking and 384-D embedding pipeline | 25-Aug-2026 | 26-Aug-2026 | Development Team | Completed | 10 | 10 | Day 5: Done; Day 6: Done
US-02 | T6 | PostgreSQL/pgvector persistence and indexing | 26-Aug-2026 | 28-Aug-2026 | Development Team | Completed | 12 | 12 | Day 6: Done; Day 7: Done
US-03 | T7 | Query Understanding Agent and routing | 28-Aug-2026 | 01-Sep-2026 | Development Team | Completed | 10 | 10 | Day 7: Done; Day 8: Done; Day 9: Done
US-04 | T8 | Retrieval Agent, Top-K ranking and filtering | 01-Sep-2026 | 03-Sep-2026 | Development Team | Completed | 12 | 12 | Day 9: Done; Day 10: Done; Day 11: Done
US-05 | T9 | Response Generation and source attribution | 02-Sep-2026 | 04-Sep-2026 | Development Team | Completed | 12 | 12 | Day 10: Done; Day 11: Done; Day 12: Done
US-06 | T10 | Sequential orchestrator and error handling | 03-Sep-2026 | 07-Sep-2026 | Development Team | Completed | 12 | 12 | Day 11: Done; Day 12: Done; Day 13: Done
US-07 | T11 | Clarification and conversation memory | 04-Sep-2026 | 08-Sep-2026 | Development Team | Completed | 10 | 10 | Day 12: Done; Day 13: Done; Day 14: Done
US-08 | T12 | Knowledge-gap and hallucination guard | 07-Sep-2026 | 09-Sep-2026 | Development Team | Completed | 8 | 8 | Day 13: Done; Day 14: Done
US-09 | T13 | Query console, trace, history and statistics | 08-Sep-2026 | 10-Sep-2026 | Development Team | Completed | 10 | 10 | Day 14: Done
US-10 | T14 | Voice interface, integration testing and final validation | 10-Sep-2026 | 11-Sep-2026 | Development Team | Completed | 10 | 10
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | 19-Aug-2026 | None | Ingestion, extraction, cleaning, chunking, embeddings and indexing.
Sprint 1 | 20-Aug-2026 | None | Ingestion, extraction, cleaning, chunking, embeddings and indexing.
Sprint 1 | 21-Aug-2026 | None | Ingestion, extraction, cleaning, chunking, embeddings and indexing.
Sprint 1 | 24-Aug-2026 | None | Ingestion, extraction, cleaning, chunking, embeddings and indexing.
Sprint 1 | 25-Aug-2026 | None | Ingestion, extraction, cleaning, chunking, embeddings and indexing.
Sprint 1 | 26-Aug-2026 | None | Ingestion, extraction, cleaning, chunking, embeddings and indexing.
Sprint 1 | 28-Aug-2026 | None | Query understanding, retrieval, response generation and agent integration.
Sprint 2 | 31-Aug-2026 | None | Query understanding, retrieval, response generation and agent integration.
Sprint 2 | 01-Sep-2026 | None | Query understanding, retrieval, response generation and agent integration.
Sprint 2 | 02-Sep-2026 | None | Query understanding, retrieval, response generation and agent integration.
Sprint 2 | 03-Sep-2026 | None | Query understanding, retrieval, response generation and agent integration.
Sprint 2 | 04-Sep-2026 | None | Query understanding, retrieval, response generation and agent integration.
Sprint 2 | 07-Sep-2026 | None | Orchestration, clarification, memory, grounding and knowledge-gap handling.
Sprint 2 | 08-Sep-2026 | None | Orchestration, clarification, memory, grounding and knowledge-gap handling.
Sprint 2 | 09-Sep-2026 | None | Orchestration, clarification, memory, grounding and knowledge-gap handling.
Sprint 2 | 10-Sep-2026 | None | UI integration, voice interface, testing, validation and documentation.
Sprint 2 | 11-Sep-2026 | None | UI integration, voice interface, testing, validation and documentation.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 19-Aug-2026 | 28-Aug-2026 | Development Team | Continue modular ingestion and validation. | Avoid delaying integration checks. | Keep modules small and test each stage. | Added validation and incremental integration.
2 | Sprint 2 | 31-Aug-2026 | 11-Sep-2026 | Development Team | Continue end-to-end agent integration and observability. | Avoid unsupported responses when evidence is weak. | Keep agent responsibilities separated and outputs structured. | Integrated orchestration, grounding, memory, testing and final validation.