## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Development Team | 24-Aug-2026 | Initial PDF ingestion required validation of extracted text and page metadata before chunking. | Sprint 1 | Development Team | Logical | Added document validation and page-aware extraction checks. | 25-Aug-2026 | Closed | Resolved during ingestion implementation.
2 | Development Team | 28-Aug-2026 | Low-confidence retrieval needed explicit handling to avoid unsupported answers. | Sprint 2 | Development Team | Logical | Added similarity filtering and insufficient-context handling. | 01-Sep-2026 | Closed | Covered by retrieval and grounding flow.
3 | Development Team | 03-Sep-2026 | Ambiguous follow-up questions needed clarification and coreference handling. | Sprint 2 | Development Team | Logical | Connected clarification and conversation-memory flow before retrieval. | 04-Sep-2026 | Closed | Verified through query-flow testing.
--- Milestone 3 Defects ---
Defect ID | Milestone | Severity | Component | Description | Root Cause | Fix | Status | Date Resolved
DEF-M3-01 | M3.2 | HIGH | retrieval_agent.py | 0 chunks retrieved on all queries | similarity_threshold default=0.0 ignored settings value, passed as None to retriever which then used 0.3 but pronoun queries yielded near-zero similarity | Changed default from 0.0 to None; added resolved_query param | CLOSED | 2026-09-23
DEF-M3-02 | M3.2 | HIGH | conversation_memory_agent.py | Pronoun it resolved to ACME (company name) instead of topic | resolve_references() used last_entities[0] = first capitalised word from LLM response (e.g. ACME CORPORATION POLICY) | Rewrote priority: active_key_terms first, filtered boilerplate from entities | CLOSED | 2026-09-23
DEF-M3-03 | M3.2 | MEDIUM | orchestrator.py | UnboundLocalError: resolved_query referenced before assignment in clarification cycle | resolved_query only assigned in else branch which was a comment, not code | Always assign: refined_query if clarification cycle, else memory_resolved_query | CLOSED | 2026-09-23
DEF-M3-04 | M3.2 | LOW | orchestrator.py | Memory-resolved query not passed to retrieval agent | resolved_query existed but was not forwarded to retrieval_agent.retrieve() | Added resolved_query parameter to retrieval agent call | CLOSED | 2026-09-23

## Sheet2
Logical
User Interface
Maintainability
Standards
Others